## Gantt
| Week2 |  |  |  |  | Week3 |  |  |  |  | Week4 |  |  |  |  | Week5 |  |  |  |  | Week6
Actions | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Check points
Design
Basic Functionality
Viable Game
Extended Game
Architecture
Data model
Object model / interfaces
Component responsibilities
Model Extension
Database
Table design
First level design
Polygon creation
Gather images
Manually enter first level
Create user path stored procedure
Create new level stored procedure
Add extra basic levels
Extra functionality
Scoreboard
Different characteristics
Floating booty
Add advanced levels
Python
Build SVG display
Database class (connection, load data)
Game classes (e.g. obstacles etc)
Website class (Jinja template, render)
Validating Route
Interface with JavaScript
Communication with stored procedures
Extensions
Scoreboard
Different characteristics
Floating booty
Website
Initial display
HTML template
Styles
Animations (Lightning etc)
Validating Route
User inputs
JavaScript python interface
Displaying success or fail
Extensions
Scoreboard
Different characteristics
Floating booty
Testing
Load and display
Validating route
Accepting extra basic levels
Extensions
Documentation
Writeup
Presentation

## Weekly
| Week2 |  | Week3 | Week4 |  |  | Week5
Display Task
Experiment Annimations, moving, lightning,explosion | MP/CC | Done | Abstract svg logic in to level and obstacles | Stored Proc Validation | ME/MP | Done | Developers page/roles | MP/CC | Low
Collect SVG images | MP/CC | Done | Create db | Slight code modifications - hit wall? | LV | Done | Code comment/cleanup - Python | ME
|  |  | wire up db | Input forms | LV | Done | Code comment/cleanup - HTML/JS | LV
Framework Task |  |  | Js/Ajax moving | Test game logic | All | Done | Level Complete modal | LV
Website Framework | ME/LV | Done |  | Note all actions done in db - tables, views, index etc Ensure have code | CC | Done | Rearrange HTML | LV
Jinja template - basic html | ME/LV | Done |  | Db system diagram (include views) | MP | Done | Description of syntax - quick input | LV
database connections | ME/LV | Done |  | Hardcode 10 moves | LV | Done | Sinking | LV
helper classes | ME/LV | Done |  | Popup saying success, click next level | LV | Done | PointerTimer | LV
Permission shared area | ME | Done |  | score input in python | ME | Done | Adjust fonts (h3) | LV
|  |  |  | jinga score param,levelid,startx,starty, max levels | ME | Done | Move styles to Marco style sheet | MP
To do |  |  |  | extend template for jinja | ME | Done | Buttons in style sheet | MP
Setup in own area | CC/LV |  |  | 100 seconds per level - countdown | LV | Done | Add h3 to css | MP
Build SVG output in level class (hard code) | MP/CC |  |  | Total score on page | LV | Done | Cleanup leaderboard | CC
polygon | MP/CC |  |  | Congratulations, you've finished - modal | LV | Done | JS error handling - testing | ME/CC
island image | MP/CC |  |  | HTML page design | MP | Done | Add intro page | MP
sea | MP/CC |  |  | Score board - db table | CC | Done | Add Nosetest as tech to PP | CC
grid | MP/CC |  |  | SQL Script for adding score with variables | CC | Done | System diagram | MP
Boat | MP/CC |  |  | add total score to db python - new entry point (addScore), add method in db | ME | Done | Object Model | ME
booty | MP/CC |  |  | Finish - - enter name, submit score - js/ajax submit | LV | Done | Make writeup outline - sections | CC
Animations |  |  |  | SQL to display top 10 scores | CC | Done | Make presentation outline - sections | CC
Move boat hardcoded path | LV |  |  | Python generate top 10 scores and add to html - jinga | MP/CC | Done
lightning | LV |  |  | Remove diamond | CC | Done
Explore Ajax/Python/parameters/move class | ME |  |  | Level 5 | CC | Done
|  |  |  | annimations | LV | Done
|  |  |  | lightning | MP | Done
|  |  |  | DB - Spatial Index - fix bug | CC | Mon
|  |  |  | Unit Tests - fix Icon | MP | Done
|  |  |  | E-R diagram - add total score | CC | Done
|  |  |  | Total Score table - db diagram | MP | Done
|  |  |  | Lightning | MP | Done
|  |  |  | explosion | MP | Done
|  |  |  | Increase points/time | LV | Done
|  |  |  | Music to stop returning on for each level | LV | Done
|  |  |  | Improve level names | CC | Done